## Cover Page
KOGI STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) & PROGRESS REPORT
State: |  | KOGI
Reporting period: |  | FY 2023
SABER Focal Person: Mukadam Asiwaju Asiru Idris FCA
List of contributing entities: | Ministry of Finance, Budget and Planning, Ministry of Commerce and Industries, Ministry of Justice, Kogi State Ministry of Works and Housing, Kogi State Internal Revenue Service, Land and Survey, Kogi State Investment Promotion Agency, Kogi State Enterprises Development Agency, Kogi State Geographic Information System
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  | 2022-11-24

## KOGI STATE ACTION PLAN
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date
1 | Improved transparency and sustainability in the property registration and land investment process | 1. identify the physical addresses of all Residences in a Classified Area/ settlements, including the physical addresses for Apartment Residents; 2. to attempt to locate the addresses for Persons who own the Residences, if they do not reside at the Residence; and 3. to attempt to locate individuals who previously resided at and/or owned a Residence within the Area during the Class. 4. Ensure Urban observatory, improve security of properties and live, aid physical planning and control, provision of physical infrastructures and a booster to revenue generation. | 1. Sensitize property owners on the need for their property records to be registered on the Kogi State Geographic Information System (KOGIS) database. 2. Publishing Radio jingles and fliers oragnizing town hall meetings 3. Carry out Property identitfications implementation across the entire State. | 1.Property Identification would be undertaken to identify the physical addresses of all Residences in a classified area/ settlements, including the persons who own the residences, or individuals who previously resided at and/or owned a residence within the area during the exercise. 2.The proposed Property identification program when implemented will ensure Urban observatory, improve security of live & properties, aid physical planning and control, and boost revenue generation. | Land and Survey | Kogi Stae Geographic Information System (KOGIS), Kogi Internal Revenue Service (KIRS), Kogi State Investment Promotion Agency (KOSIPA) | N115,000,000 | 2023-01-01 | 2023-12-01
2 | To Ease Fibre Optics Infrastructural Investments To Private Investors In Kogi State. | Improve businesses access to internet , skills and up-to-date information | Meeting with Network, providers, regulators and investors. Registration of Investors. Liscensing and Permits. Right of Way acquisition. Information Management in respect of geographical Information system. Price Regulation of unbound fibre products, Future Review. | 1. This will involve registration of investors, issuing of licences and permits for right of way acquisition by investors and regulation of prices of unbundled fibre products. | Ministry of Rural Development and Energy | Kogi State Information and Technology Agency (Kogi SITDA), Ministry of Works, Land and Survey | N123,000,000 | 2023-01-01 | 2023-12-01
3 | Increased transparency of official fees and procedures | Make the fees and rates charged as approved by State Tax Laws as amended in all revenue lines and are made known to the public and no hiden charges | The Laws, rates, fees and charges will be published in the State Website, Kogi State Government Websites and Newslettes of KGIRS, Intermittent publication and Media outing on Electronic media | All the fees that will be charged by the Ministry are contained in the State Harmonized Laws and these are the fees that will be published as contained in the Action steps | Ministry of Comerce and Industry | Kogi State Internal Revenue Service (KGIRS) | N5,000,000 | 2023-05-01 | 31/03/2023
4 | Increased Transparency of fees & levies for inter-state trade and increased export certification | Increase ease of doing business across the State | All road blocks across the State are to be dismantled as directed by the Executive Governor to ease the flow of goods and services across the states. | 1.Haulage Fees will be collected at the point of Loading and Offloading hence no road block will be allowed. 2. Export Certification has been fully automated, however, the use of the channel needs sensitization and awareness. 3. All illegal road blocks across the State must be demolished by the Law enforcement agents who will maintain free movement | Ministry of Commerce and Industry | State Vigillantee, police and Civil Defence, and Military, Ministry of Information and KGIRS | N20000000 | 2023-02-01 | 2023-12-12
5 | Simplified State and Local business tax regime | Single tax body administering tax in the State. | 1.The expired MOU between the State IRS and the 21 Local Goverment will be renewed effective January 2023. 2. The MOU will be consolidated into permanenet Law such that all revenue will be administered by the KGIRS. 3. Local Government Revenue Officers will be subjected to competency test and those who are successful will be transferred to KGIRS as Staff while the unsucessful will be moved to another department of the Local Governement. 4.A joint account where DLG and Treasurer will be signatories but a confirmation from KGIRS is made before withdrawal by the Local Government. 5. Monthly Revenue Performance meeting to be chaired by the KGIRS and Minstry of Local Government with 21 Local Government Chairmen and Treasurers as Participants will happen monthly 6. All cash collection is to be outlawed. | The reform is focused on achieving simplified tax regime that will lead to increase in IGR for both the State and the Local Government | KGIRS | Ministry of Local Government and Chieftaincy Affairs, Chairmen of the 21 Local Government | N20,000,000 | 1st January, 2023 | 12th Dec,2023
6 | Improve domestic and external trade competitiveness | Quality improvement on all products in the state with special focus on Cashew nut production and reduced cost of labour. | 1.Cashew producing farmers will be supervised by Extension workers to ensure quality harvest. 2. We will create enabling environment for Standard Organization of Nigeria to operate freely to gurantee quality 3.Grants/Aids will be given to farmers and traders through Ministry of Commmerce to qualIfying Individual or Company | Improved Quality of goods and services through Supervision of production and motivation through grants/Aids by the State. | Ministry of Commerce and Industry | Ministry of Finance, and Ministry of Agricluture | N5OO,OOO,OOO | 2023-01-01 | 2023-10-01
7 | Harmonized and more transparent State taxes | Harmonize Local Government taxes with that of the State so as to inmprove the ease of doing business, to also increase revenue accountability and increase in IGR for both state and Local Government | The State Tax Laws and the Local Governemt Revenue Laws should be merged into one document and published on the State and IRS websites . | KGIRS *After harmonization, KGIRS will be collecting tenement fees, radio and television license for the 21 Local Governments . Harmonization of tax laws with the Local Government: in addition to the other lines of revenue, Emblem is a collection of state and Local Government. This will be harmonized in the year 2023 with State IRS collecting and sharing formula will be put in place between the state and the 21 Local Government Council. | Ministry of Commerce and Industries, State House of assembly | 21 LG Chairmen | 5000000 | 2023-01-01 | Nov, 2023
8 | Quick determination of commercial disputes | Improve significantly the time spend to settle commercial disputes | 1. Establishment of Multi door Court House, Including acquisition of equipments. 2. Employment of skilled professionals and remuneration (at least 4 skilled arbitrators). 3.Remuneration of staff. 4. Public Awareness | Real Estates, Industries, Government, Civil Servants, Businesses, Farmers, Traders Target Objectives: 1. Multi door Court House is open to all manner of people in business community including artisans, petty trader, partnerships, Limited and Public Liability Companies that are involved in some forms of commercial disputes in the course of their transactions desiring quick determination of such disputes within Kogi State. 2. Employment opportunities to qualified arbitrators, reconciliatory, mediators and negotiators who are indigenes of Kogi State. 3. Employment opportunities to qualified administrative personnel, personal assistant, Secretaries, ICT personnel and other sundry staff. 4. Filling fees charged or penalties awarded against any party for defaults can generate substantial revenue for the Kogi State government | Ministry of Justice | Ministry of Commerce and Industry, High Court of justice , National Industrial Court, Taxes Appeal Tribunal . | N712,000,000 | 2023-01-01 | 2023-12-01
9 | Establishment of a skills registry and talent development | 1. Creation of a pool of knowledgeable and skilled manpower that will facilitate eGovernment practices, technology acquisition, assimilation and diffusion in public service; Increase in productivity of workforce via digital literacy. 2. Solving the conundrum around inadequacies in preparing current and potential workforce for digital economy and foster in them: • General skills for creativity • Interpersonal skills and ability to execute plans • High standards and independence • Natural inclination to further learning • Skills for relevance and competitiveness in 21st Century 3. Establishment of proficiency of workforce in digital literacy to guide policy formulation 4. Growing of economy through a vibrant ICT Sector that contributes to increased revenue; 5. Stimulation and optimization of investment and enterprise environment; 6. Development of a knowledge-based economy that is rooted in sustained human capacity development, wealth generation and job creation; 7. Improvement of operational efficiencies across government and economy-wide. | 1. Conduct of baseline assessment to establish proficiency of potential and current workforce digital literacy using the ICT Digital Literacy metrics 2. Development of Digital Literacy Strategy to bridge the identify gaps; Formulation of Policy, Setting of Standard and Guidelines 3. Development of Digital Literacy Framework and Career Certification Roadmap for - Review of curriculum at all levels of, development of framework /mapping of career and capacity skills development standards into all categories of academic programmes and levels of education and continuous professional development of all categories of workforce; 4. Establishment, Setting Up and Activation of Centers for Development of Digital Literacy and Emerging Skills as testing and certification Centers in the 6 zones of Kogi State; Implementation of Framework 5. Training and certification of all workforce at Project Office, zonal Project Offices in minimum of 3 and maximum of 5 skill areas starting with IC3 Digital Literacy in the first year; 6. Training and certification of trainers in minimum of 3 and maximum of 5 skill areas starting with IC3 Digital Literacy in the first year; | All current public service workforce, regardless of career, level or job role All Potential workforce; graduate and non-graduate job seekers; unemployed or underemployed Small and medium scale businesses. Target Objectives: Build capacity in all participants using digital tool for ease of their businesses. Apply digital tools to gather, evaluate, and use information for the ease of businesses. • Employ strategies to guide inquiry in digital environments. • Use digital tools according to disciplinary conventions and in application to business processes. • Engage proactively with digital tools in business environments. • Apply existing knowledge to generate new ideas, products, or processes in digital representation of businesses. • Use critical thinking skills to plan and conduct research, manage projects, solve problems, and make informed decisions using appropriate digital tools and resources. • Process digital data and report results. | Kogi Enterprise Development Agency and Kogi State Information and Technology Agency (Kogi SITDA) | Kogi State Ministry of Finance, Budget & Economic Planning, Kogi State Investment Promotion Agency (KOSIPA) | N563,137,259 | 2023-01-16 | 2023-10-27